## Summary
Summary
Item | Detail
What was built | Approved sign-in, OTP and returning-doctor unlock screens, built into the prototype on the draft branch only
Live link | Unchanged (nothing merged to main)
Preview link (try on your phone) | https://deploy-preview-5--doctor-portal-prototype.netlify.app
Preview status | Netlify reports the preview as ready; not opened from Claude's side
Branch / PR | doctor-portal/sign-in · draft PR #5
Decision log | D-38
Home | Unchanged; still the temporary version
Removed | Old 6-digit OTP, in-app Request access screens, separate fingerprint set-up screen
Next up | Home state 1, "Not taking cases", for review
Automated checks
Automated test suite (phone + desktop) | 536 checks, all pass (sign-in tests rewritten)
Layout check | Passes at all four screen sizes
Approved states built | 25 | Sign-in + OTP states (from the Screens & states tab)

## Screens & states
Screens & states
"Approved states / variants" is filled once per screen; blank rows are further behaviour of the same screen.
Screen | Screen key | Approved states / variants | What it does
Sign in | Sign in | 12 | Pasted numbers cleaned automatically
Sign in | Sign in |  | Keyboard closes on "not registered"
Sign in | Sign in |  | Main button becomes "Call Doctor Ops" (+91 86524 24617) for an inactive account
Sign in | Sign in |  | "Sign up" opens the onboarding web form
OTP | OTP | 13 | Keyboard closes on the 4th digit
OTP | OTP |  | "Sign in faster next time" card: unticked by default; tapping anywhere on the card ticks it
OTP | OTP |  | 5 wrong codes lock the number (D-34); going back or restarting sign-in does not reset it
OTP | OTP |  | Cap of 4 codes per number (D-35)
Faster sign-in | Faster sign-in |  | Card ticked + correct code opens a stand-in for the phone's passkey prompt; cancelling still signs the doctor in
Returning doctor | Returning doctor | 3 | Opens on "Hello, Dr. Apurva."; prompt opens when the doctor taps Unlock; fingerprint, Face ID and screen-lock versions
Home | Home |  | Unchanged; still the temporary version

## Test inputs
Test inputs
[MOCK] demo values; also listed in the prototype's demo controls.
Type | Enter | Triggers
Mobile number | Any number starting 90 | Not registered
Mobile number | 9222222222 | Inactive account
Mobile number | 9333333333 | Couldn't send
Mobile number | 9444444444 | Too many tries
OTP code | 0000 | Wrong code
OTP code | 1111 | Expired
OTP code | 2222 | Couldn't verify
OTP code | Any other 4 digits | Signs you in
Demo control | Offline | Simulates no connection
Demo control | Passkey supported | Shows or hides the faster sign-in card
Demo control | Unlock method | Fingerprint / Face ID / screen lock
Demo control | Unlock fails | Phone prompt fails
Demo control | Reset app | Clears the saved session

## Calls to check
Calls to check
Both calls 1–2 are recorded in the decision log (D-38). Fill the yellow column.
# | Call made | Why | Your decision
1 | No automatic unlock prompt: a returning doctor taps Unlock | The earlier plan opened the prompt straight away, but the approved "Ready when you are" screen implies a tap
2 | Notices differ between screens: sign-in notices are larger than OTP notices | Kept exactly as in the two approved render sets; probably worth making consistent later
3 | Also committed: Stop while a Next order request is pending | Rule added to the Home docs by the other session: the pending request is honoured, then work stops