## Sheet1
Doctors Portal Order Flow fix for Subs skip | Create right visibility on Doctors Portal for various category calls and order flows so that they can do the right expectation setting with the customer | Release went on Jun 23, Doctors now see the Right CTAs, Transfer CTA is visible only when there is a HA call happening. SOP given, doctors trained.
Skip HA call Visiblity Logic Change | We will show an option to skip HA call to all the NFTC customers. It will a default opt in option and the customer will have to opt out. Not doing any UI changes just the BE logic change | Single Skip saw a ~150% increase per day, translating to a 9.2% increase in total daily skips — strong feature adoption signal.
Renablement of NPS salt sales | We will be able to sell NPS salts on our platform with the right method with the routing of these orders to specialised Doctors | 1. Opportunity & Phase 1 scope The full NFS basket had peak sales of ~₹2 Cr/month, considering the peak sale for each category before it was stopped at different times. For Phase 1, we have picked the following four high-value categories: Rybelsus - oral Semaglutide GLP-1 injectables Pregabalin / Gabapentin ED - Sildenafil / Tadalafil / Avanafil Together, these contributed ~₹1.4 Cr/month at peak, which is the target sale for this phase. 2. Where we are today We are currently at a ~₹50 L/month run-rate, basis order digitized value. While we are scaling up, it is important to note that we have deliberately kept certain restrictions in place to ensure compliant selling of these salts. Salt Peak (₹L/mo) Serviceable under current controls (₹L/mo) What we're restricting Rybelsus (tablets) ~49 ~25 14 mg strength blocked by molecule cap (recoverable - by cap increased - initiated) GLP-1 injectables ~30 ~16 Delhi consciously not serviced - so ~14L/month sale lost Pregabalin / Gabapentin ~45 ~24 2,030 fraud-risk pincodes blocked ED new category ~6 none
Upfront payment | Shifting payments to the checkout stage for non-HA orders to create a seamless purchase experience, reduce confusion from delayed payment links, and drive higher order completion. | This is a huge analysis which is still going on
Multiple DID feature | We needed to configure multiple numbers for valuemeds and dynamically allocate these numbers for doctor calling so that even if the numbers are marked as spam we can fallback to a different number | Did not measure the impact, should have seen connectivity improvement, this is still not configurable though and is manually done via DB entry rather than automating it to fallbacks as soon as connectivity falls
Payment Revamp | Build Payment as a new service whith all the use cases covered 1. Repository setup 2. DDB Schema design 3. Payment INIT 4. Payment Process 5. INIT Refund 6. Process Refund 7. GET Payments + Integrate with Existing system 8. OMS Integration 9. Reconciliation Cron Jobs 10. Payment Consumer 11. OMS consumer 12. CI 13. Automation | Live at Scaled to 12 warehouses (50%) on Jul 9. https://truemeds.atlassian.net/wiki/spaces/~712020265c8706b18442feb9e18706a26d84dd/pages/1869971463/Payment+Service+Cutover+Review+Scale+Decision+Chennai+Raipur+Indore+Jun+2026, take all good points from here
Value Meds | Fixes to Slot creation logic for both DR and HAs and fixing the gaps between the 1st and concecuent attempts
Cost Absorption | Prices changed due to N number of reasons after the customers confirmed the order at the order summary, this feature locks the price and hence the customers sees no price shocks later
Voice Bot Phase 1 | Integration and setting up of Oration AI voice bot to handle FCR orders | Answering 22% of the total call volume on the platform
HA Subs Skip | Skip the orders , where the chances of the customer opting for substitute is lower or the value addition is lesser | Analysis yet to come
Cancellations via CSR
Fraud Fixes
COD Blocking
Prescription fixes
HA's/Doctors not able to confirm orders