## Raw Initiatives
Truemeds — Raw Initiative Inventory (Thread Handoff) | [13 empty] | Inventory Summary
Raw inventory from the Q3 roadmap discussion. This is intentionally wider than Q3 capacity; use filters before treating any row as a commitment. | [13 empty] | Metric | Value
[14 empty] | Total rows | 113
ID | Initiative | Raw Scope / Context | Source | Business Area | Likely Metric Home | Primary Driver / Outcome | Type | Latest State | Q3 Role | Dependencies / Risks | Potential Overlap / Scope Boundary | Baseline / Evidence Needed | Mapping Confidence | Committed / Required | 13
1 | Juspay integration | Integrate agreed neutral payment orchestration with the new payment service; use controlled traffic and validate lifecycle correctness. | User chat — current Q3 call-out | Payments | Online Payment Contribution | Payment completion, finality, observability | Impact | Committed | Build | Payment service path, PG/router config, event contract, support/runbook | Separate from payment-service technical revamp and prepaid-growth experiments | Payment funnel and lifecycle events | High | Candidate | 85
2 | Payment-flow changes for higher online payment contribution | Discover and test CTA, Select Payment Mode, Pay Now, reassurance, incentive, and journey changes to shift eligible cohorts from COD to online payment. | User chat — current Q3 call-out | Payments | Online Payment Contribution | Prepaid selection and completion | Experiment | Candidate | Discovery + Pilot | Order Cart/Order Summary dependency, payment funnel, experiment design | Separate from Juspay; Juspay is reliability/orchestration, not assumed prepaid uplift | Eligibility→exposure→selection→initiation→success funnel | High | Conditional / Future | 5
3 | Payment funnel instrumentation | Measure payment eligibility, CTA exposure, payment mode selection, initiation, success/failure/pending, and final order outcome by cohort. | User chat / roadmap draft | Payments | Online Payment Contribution | Decision-ready payment baseline | Foundation | Required | Foundation | Events, analytics/warehouse, experiment tags | Foundation under Online Payments; not a separate business bet | Current event coverage and payment lifecycle completeness | High | Dropped / Completed | 2
4 | Payment correctness monitoring | Monitor and fix pending, mismatch, duplicate payment, refund, paid-vs-payable and finality issues. | User chat / payment roadmap history | Payments | Online Payment Contribution | Payment correctness / support avoidance | Correctness | Active | Monitor + Fix | Payment service, OMS, refund flows, support ownership | Financial correctness hard gate as well as Payments item | Issue reason map and support-contact baseline | High
5 | Partial COD / selective COD policy exploration | Explore evidence-led partial COD, selective restrictions, or selective fees for high-risk customer cohorts; do not treat as broad rollout. | User chat — ideation | Payments | Online Payment Contribution | COD risk / prepaid uptake | Experiment | Candidate | Discovery | Policy, legal/commercial review, cohort definition, trust guardrails | Potential overlap with payment-flow experiments; should remain a separate policy experiment | Historical cancellation/RTO behavior and customer reaction | Medium
6 | Cost absorption monitoring / experiment learnings | Track effect of payment-led cost absorption and price/payable changes; use learnings for payment experience and policy decisions. | Historical Payment roadmap | Payments | Online Payment Contribution | Payment economics / guardrails | Foundation | Needs reconfirmation | Monitor | Analytics, pricing/warehouse signals | Earlier May–June work; user says upfront rollout complete | Cost absorption baseline by cohort and driver | Low
7 | Upfront payment rollout / implementation | Completed rollout work; retain only as historical context and for ongoing performance monitoring. | User chat — explicit update | Payments | Online Payment Contribution | Prepaid contribution | Impact | Completed | Monitor | None stated | Do not treat as an active Q3 build unless user reopens it | Post-rollout cohort metrics | High
8 | Payment service technical revamp | Technical revamp is stated as done; ongoing rollout/production state needs confirmation. | User chat — explicit update | Payments | Online Payment Contribution | Payment finality/reliability | Foundation | Technically complete / rollout status to confirm | Monitor | Warehouse migration status, OMS, refunds | Earlier roadmap referenced partial warehouse rollout | Live warehouse coverage and incident baseline | Medium
9 | Doctor Portal Phase 1 | Build new Doctor Portal / new service; move relevant frontend logic to backend; show Doctor only required information from onboarding through prescription and confirmation. | User chat — confirmed Q3 candidate | Doctor / Compliance | Compliance | Compliance adherence, auditability, Doctor workflow quality | Impact | Candidate / default compliance vehicle | Discovery + Build | Backend service, auth, audit evidence, clinical workflow decisions | Parent initiative; child workflow items below should be phased rather than treated as separate full builds | Doctor workflow baseline, audit failure baseline | High
10 | Doctor onboarding and credential controls | Doctor onboarding, credential management and role-based access controls. | User chat / Doctor Portal direction | Doctor / Compliance | Compliance | Identity integrity | Correctness | Candidate | Build | Auth/identity, compliance process | Likely part of Doctor Portal Phase 1 | Current onboarding / credential verification process | High
11 | Doctor identity, anti-impersonation and audit workflow | Bind Doctor identity, session, call and prescription actions; establish auditable workflow and review queue. | User chat — explicit hard gate | Doctor / Compliance | Compliance | Zero confirmed impersonation / audit coverage | Correctness | Required | Build | Authentication, call/event attribution, audit operations | May be a Doctor Portal Phase 1 component but must remain explicitly visible | Verified identity/session attribution coverage; current audit coverage | High
12 | 100% Doctor audit coverage | Ensure all Doctor interactions / prescription events are captured by an audit workflow; exact automated vs human-review policy remains open. | User chat — explicit requirement | Doctor / Compliance | Compliance | Audit coverage / Doctor quality | Correctness | Required | Build | Call recordings/evidence, audit queue, operations capacity | Overlap with anti-impersonation and Doctor Portal; retain as explicit policy outcome | Current audit coverage, audit quality score, closure SLA | High
13 | Critical Doctor/HA portal reliability and service-dependency discovery | Map recurrent portal issues, upstream/downstream dependencies, containment and observability to reduce firefighting. | User chat — explicit NFR discussion | Portal Reliability | Compliance | Critical journey reliability | Foundation | Candidate | Discovery | Engineering architecture map, incident data, observability | Cross-cuts Doctor/HA/CSR; primary home is Compliance because clinical flows are critical | Recurring issue taxonomy, incident detection/resolution time | High
14 | Mandatory patient name and age | Ensure required patient name and age are captured in Doctor workflow / prescription flow. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Prescription completeness | Correctness | Candidate | Build | Doctor Portal workflow | Likely Doctor Portal child item | Current missing-field rate | High
15 | Schedule drug visibility | Show controlled/schedule drug context in Doctor Portal where needed. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Clinical compliance | Correctness | Candidate | Build | Drug master / rules | Potential Doctor Portal child item | Current visibility/compliance gap | Medium
16 | Dosage update for Rx-required salts | Provide dosage update / edit capability for Rx-required salts. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Prescription correctness | Correctness | Candidate | Discovery + Build | Drug master, clinical logic | Potential overlap with dosage rules / prescription validation | Current exception volume | Medium
17 | Prescription validation Type 1 | Type 1 prescription validation logic. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Prescription correctness | Impact | Candidate | Discovery | Drug master, rules, definition of Type 1 | May be phase of clinical rule engine | Validation errors / current SOP outcomes | Medium
18 | Prescription validation Type 2 | Type 2 prescription validation logic. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Prescription correctness | Impact | Candidate | Discovery | Drug master, rules, definition of Type 2 | May be phase of clinical rule engine | Validation errors / current SOP outcomes | Medium
19 | Provisional diagnosis entry | Enable structured provisional diagnosis capture by Doctor. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Doctor quality / clinical record completeness | Impact | Candidate | Build | Doctor Portal | Likely Doctor Portal child item | Current diagnosis capture completeness | Medium
20 | Order type tags in Doctor Portal | Show tags/context for order type to support Doctor decision-making. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Workflow clarity / correct routing | Impact | Candidate | Build | Order service / Doctor Portal | Likely Doctor Portal child item | Current decision errors by order type | Medium
21 | Doctor quality parameters and script integration | Build quality parameters / scripts into Doctor workflow. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Doctor quality / protocol adherence | Impact | Candidate | Discovery + Build | Quality team, call workflow, audit model | Overlap with audit coverage and Doctor quality score | Quality baseline and adherence exceptions | Medium
22 | Specialist order rerouting | Route cases requiring specialist review to the correct department / specialist. | Doctor Initiatives workbook / SOP context | Doctor / Compliance | Compliance | Clinical routing correctness | Correctness | Candidate | Build | Department mapping, workflow, support escalation | Overlap with clinical routing / exception workflow | Incorrect routing baseline | Medium
23 | Intelligent medicine display and ranking | Improve how medicines are displayed/ranked to Doctor for clinical/operational decisions. | Doctor Initiatives workbook — previously surfaced | Doctor / HA | Compliance | Decision quality | Impact | Candidate | Discovery | Drug master, ranking logic | May overlap with multiple substitute options / clinical rules | Current decision time / quality data | Low
24 | Savings transparency | Show savings information appropriately in Doctor/HA workflow. | Doctor Initiatives workbook — previously surfaced | Doctor / HA | OP → OD | Customer conversation / substitution quality | Impact | Candidate | Discovery | Pricing/savings data | May be HA-facing rather than Doctor-facing | Impact on acceptance / cancellation | Low
25 | Increase share of Valid Rx | Initiatives to increase Valid Rx share / improve valid prescription capture. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Valid Rx rate / reduced clinical friction | Impact | Candidate | Discovery | Clinical process, customer flow | Outcome theme more than a single feature; needs decomposition | Current Valid Rx rate and causes | Low
26 | Drug Master creation and maintenance | Create/maintain structured Drug Master used by clinical and portal logic. | Doctor Initiatives workbook — previously surfaced | Clinical Platform | Compliance | Clinical rule reliability | Foundation | Candidate | Discovery | Data ownership, CMT, clinical governance | Foundational dependency for several clinical items | Data completeness/quality | Medium
27 | Clinical Rule Engine | Rule engine for clinical/doctor prescription logic. | Doctor Initiatives workbook — previously surfaced | Clinical Platform | Compliance | Clinical correctness / scalable controls | Foundation | Candidate | Discovery | Drug Master, rule governance, engineering scope | Large platform capability; do not imply Q3 full build | Rule inventory and exception volume | Medium
28 | Dosage-form instruction logic | Apply instructions based on dosage form. | Doctor Initiatives workbook — previously surfaced | Clinical Platform | Compliance | Prescription correctness | Impact | Candidate | Discovery | Drug Master / rule engine | Clinical-rule-engine child candidate | Current instruction exceptions | Low
29 | Chronic prescription logic | Chronic prescription / refill-related clinical logic. | Doctor Initiatives workbook — previously surfaced | Clinical Platform | Compliance | Clinical correctness / retention | Impact | Candidate | Discovery | Drug Master / clinical rules | Potential later phase | Cohort definition and current outcomes | Low
30 | Contraindication checks | Add contraindication checks in clinical flow. | Doctor Initiatives workbook — previously surfaced | Clinical Platform | Compliance | Clinical safety | Correctness | Candidate | Discovery | Drug Master, clinical governance | Potential rule engine item | Current contraindication exception data | Medium
31 | Medicine capping | Implement medicine caps / quantity guardrails. | Doctor Initiatives workbook — previously surfaced | Doctor / Compliance | Compliance | Clinical/compliance control | Correctness | Candidate | Discovery + Build | Rules, category definitions | Potential overlap with max-quantity portal fixes | Current cap breaches | Medium
32 | Multi-patient prescription handling | Enable separate prescription handling for medicines required by multiple patients. | User chat — explicit Doctor pain | Doctor / Compliance | Compliance | Prescription correctness | Impact | Candidate | Build | Doctor Portal | Likely Doctor Portal Phase 1 child | Current multi-patient failure/exception rate | High
33 | Repeat Order Kitty logic | Repeat order logic referenced in Doctor initiative inventory. | Doctor Initiatives workbook — previously surfaced | Doctor / Retention | Retention | Repeat purchase / workflow | Impact | Needs clarification | Discovery | Business definition | Name/context unclear; preserve without assumptions | Definition and current behavior | Low
34 | Doctor-to-HA information passing | Pass Doctor call information / context to HA for downstream consultation. | Attached feature PDF / user chat | Doctor / HA | OP → OD | Handoff quality / call-to-confirmation | Impact | Candidate | Build | Doctor Portal/HA portal, call context | May be broader than simple notes visibility | Handoff errors / HA repeat questioning | High
35 | Doctor call cancellation controls | Control / digitalize cancellation behavior in Doctor call workflow. | Doctor compliance FRD / prior context | Doctor / Compliance | Compliance | Auditability / correct order state | Correctness | Candidate | Build | Doctor workflow, OMS/order states | Overlap with digital cancellation and compliance workflow | Cancellation audit baseline | Medium
36 | Doctor/HA contact baseline and actual attempt capture | Capture actual first/second/etc. dials, connection, actor, timestamp, outcome, and next action instead of assumed attempts. | User chat — explicit problem | Contact Operations | OP → OD | First-call pickup, successful connection, TAT | Foundation | Required | Build | Telephony events, portal/assignment events, data model | Supports OP→OD and CPO but should be housed under OP→OD | Current event coverage | High
37 | Missed Doctor/HA call recovery | Replace callback toast → CSR dead-end with order-aware customer callback, HA-first live transfer or correct callback queue/slot. | User chat — explicit quick win | Contact Operations | OP → OD | Missed-call recovery / successful connection | Impact | Candidate | Build | Order state, role availability, telephony, callback routing | Doctor live transfer has stronger clinical/availability constraints than HA | Current missed-call and callback funnel | High
38 | Customer-first pre-connect experiment | Call customer first / establish pickup, then ring Doctor or HA only after connection; start with Doctor first-connect baseline and limited experiment. | User chat — explicit experiment | Contact Operations | OP → OD | First-connect / discard reduction | Experiment | Candidate | Discovery + Pilot | Telephony, spam risk, customer experience | Potential overlap with pull-call and missed-call recovery; different hypothesis | First-call pickup and pre-connect acceptance | High
39 | Pull-call / customer-initiated / slot-based calling | Test customers calling or scheduling HA contact instead of only outbound agent calls; HA-first because Doctor calls have legal/clinical constraints. | User chat — explicit ideation | Contact Operations | OP → OD | Connectivity / customer wait | Experiment | Candidate | Discovery + Pilot | Availability, slots, callback routing, customer adoption | Potential overlap with missed-call recovery but broader customer-initiated model | Customer willingness and conversion baseline | High
40 | Doctor/HA demand-supply mapping | Define eligible order demand and Doctor/HA supply by role, availability, skill/language, capacity, and priority. | User chat — strategic direction | Contact Operations | OP → OD | Correct contact routing / throughput | Foundation | Candidate | Discovery | Availability data, eligibility, queueing/routing | Future platform direction; not full Q3 marketplace promise | Demand, supply, wait time and capacity baseline | High
41 | Connectivity and number-health improvement | Understand and improve connectivity without spam marking: number health, rotation/enable-disable calendar, ops self-serve, monitoring. | User chat / Truecaller material | Contact Operations | OP → OD | First-call pickup / number reputation | Impact | Candidate | Discovery + Execution | Telephony provider, DIDs, operations controls, Truecaller | Umbrella for related connectivity subitems below | First pickup, spam marks, number performance by DID | High
42 | Truecaller / Ozonetel directory and whitelisting | Register/verify caller identity, whitelist Ozonetel numbers where possible, add Truemeds directory presence. | Vineet Truecaller / user chat | Contact Operations | OP → OD | Caller trust / pickup | Impact | Candidate | Execution | Truecaller/Ozonetel / operations | Child of connectivity/number health | Pickup and spam baseline by number | High
43 | DLT/spam classification reduction | Reduce spam classification / caller reputation issues through relevant operational and telephony controls. | Vineet Truecaller — previously surfaced | Contact Operations | OP → OD | First-call pickup | Impact | Candidate | Discovery + Execution | DLT, telco, operations | Child of connectivity/number health | Spam complaint/classification data | Medium
44 | DID / connection quality monitoring | Track DID performance and connection quality. | Vineet Truecaller — previously surfaced | Contact Operations | OP → OD | Connectivity / number health | Foundation | Candidate | Build | Telephony data | Child of connectivity/number health | DID-level connection baseline | Medium
45 | First connection rate tracking | Establish first connection / first-call pickup rate for Doctor and HA flows. | Vineet Truecaller / user chat | Contact Operations | OP → OD | First-call pickup | Foundation | Required | Build | Actual attempt ledger and telephony | Part of contact baseline; retain separately as visible metric requirement | Current first-connect baseline | High
46 | Global DND / customer contact preferences | Create global DND / preference controls; define exceptions for mandatory transactional/clinical communication. | User chat — ideation | Contact Operations | Trust & Retention | Customer trust / complaint reduction | Foundation | Candidate | Discovery | Policy, consent, channel preferences | Could become broader preference centre; not a generic marketing DND | Contact frequency, opt-out and complaints | Medium
47 | Personalized / repeat-customer contact experience | Use customer history, accepted substitutions, preferences and repeat behavior to improve experience. | User chat — ideation | Contact Operations | Trust & Retention | Retention / customer trust | Experiment | Candidate | Discovery | Customer history, preferences, substitution ledger | Umbrella concept; needs narrow use-case selection | Repeat customer behavior | Low
48 | HA multiple substitute options | Show more than one appropriate substitute option for original medicine so HA can have a better customer conversation. | User chat — explicit HA pain | HA Workflow | OP → OD | Substitute acceptance / call conversion | Experiment | Candidate | Discovery + Build | Substitute catalog/ranking, clinical eligibility | May pair with No-Subs-Taken history and savings context | Offer/accept/reject/cancel outcome baseline | High
49 | No Subs Taken Reason capture and reuse | Capture structured reason for not accepting substitute and surface it during future calls to a new agent. | User chat — named project | HA Workflow | Trust & Retention | Substitution quality / later retention | Impact | Candidate | Build | Portal storage, reason taxonomy, customer history | May be a simple persistence feature or foundation for broader substitution intelligence | Reason distribution and later customer behavior | High
50 | False-substitution cancellation tracking | Measure cancellation when substitutions are made despite lack of customer interest or poor fit. | User chat — explicit causal issue | HA Workflow | OP → OD | Cancellation guardrail | Foundation | Required | Build | Substitute decision/event data | Metric/data initiative; not standalone customer-facing feature | Substitute accepted/declined and cancellation linkage | High
51 | Substitute retention baseline | Measure whether customers who accept substitutes continue buying / reorder appropriate treatment later. | User chat — explicit missing metric | HA Workflow | Trust & Retention | Retention | Foundation | Candidate | Build | Order history, medicine/substitute linkage, relevant treatment window | Not simply repeat purchase; attribution design needed | Accepted substitute to later order linkage | High
52 | Quantity flexibility for HAs | HA-side quantity flexibility / related workflow change. | Doctor Initiatives workbook — previously surfaced | HA Workflow | OP → OD | Order confirmation / customer fit | Impact | Candidate | Discovery | Order rules, prescription, pricing | May overlap with quantity mismatch portal fixes | Current failure/exception volume | Low
53 | OTC recommendation engine | Recommend OTC additions / suggestions in HA workflow. | Doctor Initiatives workbook — previously surfaced | HA Workflow | OP → OD | Order conversion / order value | Impact | Candidate | Discovery | Catalog/recommendation logic | Not core Q3 unless capacity permits | Attach and conversion baseline | Low
54 | ETA-based scheduling for not-picked orders | Schedule or route orders based on ETA / not-picked status. | Doctor Initiatives workbook — previously surfaced | HA Workflow | OP → OD | Timely contact / order progression | Impact | Candidate | Discovery | Order state/ETA data | Potential overlap with demand-supply routing | Pending order aging | Low
55 | Doctor availability tracking | Track Doctor availability for routing/scheduling. | Doctor Initiatives workbook — previously surfaced | Contact Operations | OP → OD | Connection / TAT | Foundation | Candidate | Discovery | Presence/availability data | Foundation for callback slots / routing | Availability and wait time baseline | Medium
56 | Gibberish name / wrong address detection | Detect obviously invalid customer name/address signals. | Doctor Initiatives workbook — previously surfaced | Order Quality | OP → OD | Discard/cancellation prevention | Experiment | Candidate | Discovery | Customer/order data quality | Could be delivery/fulfilment cross-team | Invalid data and order outcome baseline | Low
57 | Order Pending page revamp | Improve pending-order view/workflow. | Doctor Initiatives workbook — previously surfaced | HA Workflow | OP → OD | TAT / pending management | Impact | Candidate | Discovery | Portal UI, state data | Potential overlap with routing / demand-supply | Pending aging and action baseline | Low
58 | Customer-contact and CPO baseline | Create order/contact/case model and CPO cuts; establish contacts/order, FCR, AHT, repeat contacts, actor/channel outcomes. | User chat / roadmap draft | Customer Care | CPO | CPO driver visibility | Foundation | Required | Build | Kapture, internal portal, telephony, Finance inputs, data/analytics | Umbrella baseline; child items below should be used for implementation scope | Current event/data coverage | High
59 | Kapture-to-order mapping | Map each order-related call/ticket/chat to primary order ID, while separating non-order contacts. | User chat — explicit requirement | Customer Care | CPO | Contacts/order and case context | Foundation | Required | Build | Kapture, order service, identity matching | Foundational item for CSR decisioning, FCR, chatbot and CPO | Mapping coverage and error rate | High
60 | Kapture case taxonomy | Define contact reason, sub-reason, resolution, escalation, next action, and order/non-order taxonomy. | User chat — explicit requirement | Customer Care | CPO | FCR / AHT / repeat-contact visibility | Foundation | Required | Build | Kapture configuration, Ops SOP harmonization | Part of Customer Care baseline but useful as standalone delivery | Current reason quality and missing/outcome rates | High
61 | CSR actioning in Kapture | Give CSRs relevant order context, refund tickets and priority actions in Kapture; enable eligible action instead of only viewing data. | User chat — explicit Q3 call-out | Customer Care | CPO | FCR / AHT / refund TAT | Impact | Candidate | Discovery + Build | Kapture, payment/refund services, access controls | Needs specific action scope; do not equate with generic portal access | CSR task and escalation baseline | High
62 | FTC refund handling | Separate refund workflow described as FTC; agents see order/customer attributes/scores and a complex SOP to decide refund eligibility. | User chat — explicit | Customer Care | Trust & Retention | Refund decision quality / FCR | Impact | Candidate | Discovery | Refund policy, signals, action backend | Keep separate from return refund decisioning until logic confirmed | Current decision reasons and outcomes | High
63 | Customer return refund decisioning | Build product-led decisioning from customer/order signals so agent knows whether to refund without cognitive load. | User chat — explicit | Customer Care | Trust & Retention | Refund decision quality / TAT | Impact | Candidate | Discovery + Build | Return policies, risk signals, refund APIs | Related to FTC but currently a separate workflow | Decision outcomes, exceptions, override rate | High
64 | CSR refund intelligence / guided decisioning | Broader product direction: visible attributes + decision tree + recommended/eligible refund action. | User chat / prior inventory | Customer Care | Trust & Retention | Refund decisioning / FCR | Foundation | Candidate | Discovery | Kapture mapping/taxonomy, policies, actions | Umbrella capability covering FTC and returns decisions; preserve subflows separately | Decision tree and override baseline | Medium
65 | L2/L3 accountability flow | Move email-based L2/L3 tickets into Kapture, then accountable Confluence/Jira flow. | User chat — explicit Q3 call-out | Customer Care | CPO | Escalation accountability / resolution time | Impact | Candidate | Build | Kapture, Confluence/Jira, ownership model | Could be phased by top reason/case type | Email case volume, aging, ownership baseline | High
66 | Remove CSR dependency on Pharmacist Portal | Build role-specific CSR access/workspace so agents do not need the shared Pharmacist Portal for core work. | User chat — explicit direction | Customer Care | CPO | AHT / tool switching / access correctness | Foundation | Candidate | Discovery | Kapture, internal APIs, role/access design | Reverses earlier idea of giving broad Pharmacist Portal access; do not treat as permanent access grant | Current portal switching and task inventory | High
67 | CSR gratification access | Empower CSR with TM Rewards/Credit related tools for eligible customer situations. | CSR Empowerment sheet — previously surfaced | Customer Care | Trust & Retention | FCR / customer trust | Impact | Candidate | Discovery | Wallet/credit controls, policy | May be part of role-specific CSR workspace | Current manual handling / exceptions | Medium
68 | CSR Doctor Portal integration | CSR access/actions for patient detail correction, digitized cancellations and Doctor-call stuck orders. | CSR Empowerment sheet — previously surfaced | Customer Care | CPO | FCR / escalation reduction | Impact | Candidate | Discovery | Doctor workflow, access controls, order state | Could be handled via Kapture action layer rather than direct Doctor Portal access | Current stuck-order and correction volume | Medium
69 | Cashfree payment/refund visibility for CSR | Historical ask for payment/refund status visibility in support workflow. | CSR Empowerment sheet — previously surfaced | Customer Care | CPO | FCR / payment trust | Foundation | Needs reconfirmation | Discovery | Payment service/Juspay path, Kapture | Cashfree naming is likely stale after agreed Juspay direction; recast as payment/refund visibility | Payment/refund contact baseline | Medium
70 | Order lifecycle stage-wise journey visibility | Show case/order lifecycle stage to CSR. | CSR Empowerment sheet — previously surfaced | Customer Care | CPO | Context / AHT / FCR | Foundation | Candidate | Build | Order lifecycle data, Kapture | Could be a component of Kapture context workspace | Current missing context / tool switch rate | Medium
71 | CSR decision tree tooling | Guided next-best action / decision tree in agent workflow. | CSR Empowerment sheet / user chat | Customer Care | CPO | FCR / consistency | Foundation | Candidate | Discovery + Build | Kapture context, policy, action APIs | Primary future chatbot foundation as well | Top contact reasons and decision variability | High
72 | Chatbot foundation | Prepare context, decisioning, taxonomy and action layer for chatbot; last priority. | User chat — explicit | Customer Care | CPO | Self-service / low cost resolution | Foundation | Last priority | Conditional Discovery | Kapture mapping, decision trees, action APIs | Do not begin a broad chatbot build before case/context/action basics are ready | Top automatable reasons and containment baseline | High
73 | Returns & Refunds Milestone 1 — app-first initiation | Scale Return Tracker / app journey so customers create return/refund requests in-app rather than relying on inbound calls. | User chat — explicit milestone | Returns & Refunds | Retention | App self-service adoption / inbound call reduction | Impact | Candidate | Build + Scale | Return Tracker, app, policy, operations | Milestone 1 of larger journey | Inbound vs app request baseline | High
74 | Returns & Refunds Milestone 2 — evidence, status, eligibility and decisioning | Add image/evidence, status, eligibility and decisioning to reduce outbound/manual work. | User chat — explicit milestone | Returns & Refunds | Retention | Refund TAT / manual touches | Impact | Candidate | Discovery + Build | Return policy, customer comms, workflow | Milestone 2 | Outbound calls/case and decision exceptions | High
75 | Returns & Refunds Milestone 3 — low-risk refund automation | Automate refund processing for low-risk cases; retain inspection/warehouse/human exception flows. | User chat — explicit milestone | Returns & Refunds | Retention | Refund TAT / automation | Experiment | Candidate | Discovery | Risk rules, policy, inspection/warehouse state | Milestone 3; needs robust guardrails | Automation eligibility / error and reversal baseline | High
76 | Customer-facing refund status and communication | Clear customer status and communication to reduce uncertainty and repeat contacts. | User chat / roadmap draft | Returns & Refunds | Retention | Trust / repeat contacts | Impact | Candidate | Build | Return/refund lifecycle and notification system | Likely part of Returns Milestone 2 | Repeat-contact reasons and status visibility gap | Medium
77 | TM Wallet correctness | Fix wrong balance, ledger, expiry and visibility in TM Rewards / Credits experience for customer and agent. | User chat / complaint attachment context | Wallet | Retention | Wallet correctness / trust | Correctness | Candidate | Fix | Wallet ledger, app, CSR visibility | Financial correctness hard gate as well as trust item | Wallet error taxonomy and support volume | High
78 | Ring AI Pilot — M1 integration foundation | Eligibility, bot ownership, vendor payload, outcomes, event logging; non-negotiable pilot foundation. | Ring PRDs | Assisted Commerce | Ring Agent Conversion | Qualification / safe execution | Pilot | Committed | Pilot | Ring vendor, internal API, ownership lock, telemetry | Part of Ring programme; not a separate business bet | Eligible leads, reach, bot outcomes | High
79 | Ring AI Pilot — M2a latest-state validation and async agent routing | Re-check lead state; normalized outcome; route actionable qualified leads to agents through async pull/list model. | Ring PRDs | Assisted Commerce | Ring Agent Conversion | Agent conversion / clean handoff | Pilot | Committed baseline | Pilot | Latest-state checks, routing, agent query/pickup rules | Current preferred MVP direction; not a live-transfer marketplace | Qualified-lead to human-agent conversion | High
80 | Ring AI Pilot — M2b live transfer | Conditional live-transfer routing after discovery validates telephony, availability, and safety. | Ring PRDs | Assisted Commerce | Ring Agent Conversion | Handoff latency / conversion | Pilot | Conditional | Discovery | Telephony, availability, live transfer design | Conditional; do not promise in pilot | Transfer eligibility, queue availability, drop rate | High
81 | Ring AI Pilot — M3 configurability and operational controls | Future config / operational control layer after pilot foundations. | Ring PRDs | Assisted Commerce | Ring Agent Conversion | Scalability / operations | Foundation | Future | Discovery | Control plane, config, operations | Not MVP | Pilot learnings | High
82 | Ring agent conversion and recovery measurement | Measure human-agent conversion from Ring-qualified leads, overall abandoned-cart recovery, human effort per recovered order, lead ageing and guardrails. | User chat / Ring PRDs | Assisted Commerce | Ring Agent Conversion | Evidence-based scale decision | Foundation | Required | Build | Event correlation across bot, human, lead and placed order | Metric layer for all Ring milestones | Current manual assisted-commerce conversion baseline | High
83 | HA unable to add original medicine when 'All medicines not prescribed' | Portal fix for HA workflow. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Order completion / exception reduction | Correctness | Candidate | Fix | Portal, prescription rules | Raw fix; may be grouped into prescription change/quantity suite later | Issue volume and outcome impact | Medium
84 | Prescribed quantity greater than order quantity | Handle mismatch where prescribed quantity exceeds order quantity. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Order completion / exception reduction | Correctness | Candidate | Fix | Order/prescription rules | Raw fix; may group with quantity mismatch suite | Issue volume | Medium
85 | Order quantity greater than prescribed quantity | Handle mismatch where order quantity exceeds prescribed quantity. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Order completion / exception reduction | Correctness | Candidate | Fix | Order/prescription rules | Raw fix; may group with quantity mismatch suite | Issue volume | Medium
86 | Max allowed quantity breach handling | Handle max allowed quantity breach between original and substitute / relevant order flows. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | Compliance | Compliance / order correctness | Correctness | Candidate | Fix | Rules, prescription / substitutions | Potential overlap with medicine capping | Breach volume | Medium
87 | Customer request to change to COD | Handle customer request to change payment mode to COD. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | Online Payment Contribution | Payment flow / support handling | Correctness | Candidate | Fix | Payment/order state | May be a payment journey/ops exception rather than portal standalone | Request volume and outcomes | Medium
88 | Language barrier handling | Improve language-handling in portal / contact workflow. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Successful connection / call conversion | Impact | Candidate | Discovery | Language data, routing | May belong in demand-supply / contactability design | Language-related disconnect/low conversion baseline | Low
89 | Add secondary number flow | Allow/add secondary customer number in the relevant portal flow. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Contactability | Impact | Candidate | Build | Customer contact data | May be a quick fix within connectivity | Secondary number use and pickup baseline | Medium
90 | Medicine enablement request handling | Support medicine enablement requests in portal workflow. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Order conversion / exception handling | Correctness | Candidate | Fix | Catalog/CMT dependencies | Needs exact business context | Request volume / outcome | Low
91 | Zero attempts on valid orders | Investigate/fix valid orders receiving zero call attempts. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Call-required conversion / discard reduction | Correctness | Candidate | Fix | Assignment, attempt ledger, queue | Directly related to actual attempt capture | Zero-attempt rate by cohort | High
92 | Null category for orders with savings value > 0 | Fix category null classification for eligible saving-value orders. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Correct routing / substitution opportunity | Correctness | Candidate | Fix | Categorisation logic | Potential relation to dynamic categorisation | Null-category rate and outcome | Medium
93 | Order not confirmed after call >50 seconds | RCA/fix for orders not confirmed despite a call longer than 50 seconds. | Vineet May–June ask — previously surfaced | Pharmacist / HA Portal | OP → OD | Call-to-confirmation | Correctness | Candidate | Fix | Call event / order state integration | Potential event/state reliability issue | Long-call unconfirmed rate | High
94 | Revisit 20-attempt confirmation logic | Review existing 20-attempt logic. | Vineet May–June ask — previously surfaced | Contact Operations | OP → OD | Attempt efficiency / customer contact burden | Experiment | Candidate | Discovery | Actual attempt ledger, policy | Should not be changed before real attempts are measured | Attempt distribution and conversion | High
95 | Separate JIT vs non-JIT attempt logic | Create separate attempt logic for JIT/non-JIT order flows. | Vineet May–June ask — previously surfaced | Contact Operations | OP → OD | Attempt efficiency / TAT | Experiment | Candidate | Discovery | Order type/state, attempts | Potential follow-on to attempt ledger | Conversion/aging by JIT cohort | Medium
96 | Portal operational reporting and RCA | Business pushes for root-cause / portal solution rather than only a Metabase card; includes operational reporting reliability. | User chat / Order TAT PDF | Portal Reliability | CPO | Operational visibility | Foundation | Candidate | Discovery | Portal/reporting data, analytics | Umbrella for TAT/fill rate/generic deletion items | Current report gaps/usage | Medium
97 | Order TAT visibility | Operational visibility/reporting for order TAT. | Order TAT PDF — previously surfaced | Portal Reliability | OP → OD | TAT / pending order management | Foundation | Candidate | Discovery | Order events | Child of operational reporting/RCA | TAT baseline | Medium
98 | Order fill-rate visibility | Operational fill-rate visibility/reporting. | Order TAT PDF — previously surfaced | Portal Reliability | OP → OD | Fulfilment visibility | Foundation | Candidate | Discovery | Order / inventory data | May be outside direct pod control | Fill-rate data quality | Low
99 | Generic deletion RCA | Root-cause analysis / fix for generic deletion behavior. | Order TAT PDF — previously surfaced | Portal Reliability | OP → OD | Order correctness / exception prevention | Correctness | Candidate | Discovery | Portal/order rules | Child of operational reporting/RCA | Deletion incidence/outcome | Low
100 | Primary-secondary packaging | Heavy discovery: define complete scope and touchpoints; delayed historically and now has high delivery pressure. | User chat — explicit | CMT / Catalog | Compliance | Catalog / packaging correctness | Foundation | High pressure / scope unclear | Discovery | CMT, pack hierarchy, inventory/pricing/operations | Do not imply simple UI change or Q3 full build | Touchpoint map and scope baseline | High
101 | Temperature mapping attribute capture | Add structured storage-temperature attribute during SKU/product creation; one-time data cleanup already completed. | User chat — explicit | CMT / Catalog | Compliance | Catalog correctness | Correctness | Candidate | Build | CMT product creation flow | User clarified scope is attribute capture/storage only; no downstream logistics scope assumed | Current missing attribute rate | High
102 | Category X / not-for-sale drug enablement | Compliance-heavy enablement of currently restricted/not-for-sale drugs; stated CXO priority with estimated 1–1.5 Cr/day sales unlock. Requires all compliance-related fixes. | User chat / Not-for-sale drugs doc | CMT / Compliance | Compliance | Compliance / revenue enablement | Impact | P0 / CXO-driven | Build + Discovery | Clinical rules, Doctor assignment, Rx, max quantity, HA/warehouse/substitution/returns/invoice rules | Large multi-touchpoint initiative; do not reduce to catalog toggle | Eligible drug/order baseline and compliance exception map | High
103 | Bulk upload validation extensibility | Previously discussed CMT bulk-upload validation for new dosage forms; user asked to forget/deprioritise this item. | User chat — explicit | CMT / Catalog | TBD | N/A | Correctness | Dropped / do not plan | Defer | CMT validations | Retain only to avoid reintroducing accidentally | N/A | High
104 | MyRx manual pilot / POC | Create bulk test orders and hit MyRx API through Postman bulk runner; validate operational/API feasibility before integration. | User chat / Vineet MyRx | External Integration | OP → OD | Order confirmation / operational feasibility | Pilot | Candidate | Pilot | Analyst query/export, Postman, MyRx vendor, manual Doctor Portal action | Not integration yet | Pilot results, SLA/reachability/response quality | High
105 | MyRx integration readiness | Integrate MyRx with internal systems only after manual POC is proven. | User chat / Vineet MyRx | External Integration | OP → OD | Scalable confirmation flow | Foundation | Conditional | Discovery | Successful POC, APIs, vendor/legal/SOP | Separate from manual pilot | POC success and integration requirements | High
106 | Configurable AI / CRM adapter layer | Replace hacky wrappers over internal APIs with configurable adapter/context/action layer that can serve Assisted Commerce, customer agents, bots and future Doctor/HA use cases. | User chat — strategic direction | Platform / AI | CPO | AI enablement / scalable integrations | Foundation | Candidate | Discovery | Internal APIs, contracts, security, vendor patterns | Longer-term platform direction; do not promise full Q3 build | Current wrapper/API inventory and reuse cases | Medium
107 | Oration AI customer-care integration | Move beyond hacky current exposure; use appropriate context, decisioning and action contracts for inbound customer support AI. | User chat — strategic direction | Customer Care / AI | CPO | Automation / lower human resolution load | Foundation | Candidate | Discovery | Kapture mapping, case taxonomy, adapter, policy/action APIs | Depends on Customer Care foundation | Current Oration containment/resolution and failure baseline | Medium
108 | CSR customer-contact dashboard / baseline | Baseline calls/tickets/chats per order, order vs non-order reasons, FCR, AHT, repeat contacts and resolution outcomes. | User chat — explicit | Customer Care | CPO | CSR productivity / CPO | Foundation | Required | Build | Kapture mapping, telephony, analytics | Part of customer-contact/CPO baseline but separate delivery artifact | Current metric availability | High
109 | Customer/agent order context workspace | Show relevant customer, order, payment, return, wallet and contact history in one case workflow. | User chat — explicit target state | Customer Care | CPO | FCR / AHT / tool switching | Impact | Candidate | Discovery + Build | Kapture, internal APIs, access control | May subsume parts of CSR portal/Kapture actioning | Current tool switches and agent time | High
110 | Role-specific portal design | Reduce clutter from shared portal by showing each role only what is required. | User chat — explicit | Portal Architecture | CPO | Productivity / correctness | Foundation | Candidate | Discovery | Role access, service boundaries, new Doctor Portal, CSR workspace | Broader than Doctor Portal alone | Role-task inventory and error patterns | Medium
111 | Customer callback / direct 'continue your order' entry point | Customer initiated path after missed contact to active order action; could route to HA live/callback/payment status depending on state. | User chat — quick-win discussion | Contact Operations | OP → OD | Missed-call recovery | Impact | Candidate | Build | Order state, telephony, availability | Detailed form of missed Doctor/HA call recovery | Callback funnel | High
112 | Category dynamic categorisation for substitute pitching | Improve categorisation so best orders go to best HAs and better substitute pitching is possible. | User chat — earlier context | HA Workflow | OP → OD | Substitution quality / agent conversion | Foundation | Candidate | Discovery | Order categorisation, signals, routing | Related to demand-supply/routing and null category fix | Category quality and conversion by HA | Medium
113 | Regular customer / repeat-customer experience | Tailor journeys for repeat customers, potentially using past substitution/payment/contact behavior. | User chat — ideation | Customer Experience | Retention | Retention | Experiment | Candidate | Discovery | Customer history and segmentation | Broad concept; needs narrow initial use case | Repeat customer behavior | Low

## Legend & Context
How to use this raw inventory
Purpose | This is an intentionally broad inventory from the conversation and referenced working documents. It is not a Q3 commitment list. | Q3 Business Bet | Primary Metric | Notes
Recommended filter order | 1) Latest State, 2) Likely Metric Home, 3) Q3 Role, 4) Mapping Confidence, 5) Dependencies / overlap. | Compliance | Compliance | Hard gate: Doctor quality, anti-impersonation, auditability, prescription / financial correctness.
Metric homes | Compliance; OP → OD; CPO; Online Payment Contribution; Retention; Ring Agent Conversion. A row can have secondary impact, but this file assigns one primary home. | OP → OD | OP → OD | Delivered orders ÷ total placed orders. Track discard/cancellation with same placed-order denominator.
Types | Impact = directly expected to move the outcome; Foundation = baseline/control/enabler; Experiment = hypothesis test; Correctness = existing critical issue; Pilot = controlled live trial. | CPO & Productivity | CPO | Finance definition still needs confirmation; productivity and support resolution are key drivers.
Latest-state warning | Older attachments may be stale. Latest user statements override historical roadmap material. In particular: upfront-payment rollout is complete; payment technical revamp is stated as done; Juspay is agreed and needs to start. | Online Payments | Online Payment Contribution | Successfully prepaid orders ÷ payment-eligible orders; OP→OD is secondary guardrail.
Quarter naming | The planning period is Q3 (July–September). Existing draft workbook title using Q2 is a naming mistake to correct. | Trust & Retention | Retention | Repeat purchase / retention; refund, Wallet, substitute quality and repeat contacts are drivers.
Notable unresolved items | Finance CPO definition; exact Q3 capacity; exact scope of 100% Doctor audits; current payment production rollout coverage; FTC refund decision boundaries; return/refund volume snapshot revalidation. | Ring AI Pilot | Ring Agent Conversion | Separate non-negotiable carryover: placed orders ÷ Ring-qualified leads assigned to agents.