## Q2 Roadmap
Q2 Product Roadmap — Draft | [9 empty] | Roadmap Summary
Outcome-led roadmap across Compliance, OP → OD, CPO & Productivity, Online Payments, Trust & Retention, and Ring AI Pilot. | [9 empty] | Hard gates | 1 | Compliance
[10 empty] | Business bets | 4 | Outcome-led
Section | Primary Outcome Metric | Output Metrics | Initiative | Type | Q2 Role | July | August | September | Q2 Output / Decision | Carryover pilots | 1 | Ring AI
Hard Gate: Compliance & Doctor Quality | 100% auditable Doctor interactions; zero confirmed impersonation | Audit coverage, Doctor quality score, prescription completeness, compliance exceptions | Doctor Portal Phase 1 — new service, move frontend logic to backend, role-based Doctor workflow from onboarding to prescription | Impact | Discovery + Build | Phase 1 scope, architecture, milestones | Build priority workflows | Controlled rollout / readiness gate | Phase 1 MVP and Q3 rollout plan
Hard Gate: Compliance & Doctor Quality | 100% auditable Doctor interactions; zero confirmed impersonation | Audit coverage, Doctor quality score, prescription completeness, compliance exceptions | Doctor identity, anti-impersonation and audit workflow | Correctness | Build | Define identity, session, call and Rx attribution | Build audit workflow and review queue | Audit coverage measurement | 100% coverage design operationalised
Hard Gate: Compliance & Doctor Quality | 100% auditable Doctor interactions; zero confirmed impersonation | Audit coverage, Doctor quality score, prescription completeness, compliance exceptions | Critical Doctor/HA portal reliability and service-dependency discovery | Foundation | Discovery | Map critical failures and dependencies | Define containment / observability fixes | Prioritised reliability backlog | Q3 reliability plan
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | Doctor/HA contact baseline and actual attempt capture | Foundation | Build | Define event model and baseline cuts | Launch tracking | Review cohorts and gaps | Reliable first-call, attempt and TAT baseline
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | Missed Doctor/HA call recovery | Impact | Build | Scope order-aware callback flow | Launch HA-first callback / routing | Measure and iterate | Replace dead-end callback-to-CSR flow
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | Connectivity and number-health improvement — spam control, Truecaller/OzonTel directory, Ops visibility | Impact | Discovery + Execution | Current number-health baseline and external setup | Implement selected controls | Measure pickup / spam impact | Measurable connectivity improvement plan
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | Customer-first pre-connect / pull-call / slot-based calling | Experiment | Discovery + Pilot | Design hypothesis and eligible cohorts | Small HA-first pilot | Evaluate | Scale / stop / Q3 scope
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | Doctor/HA demand–supply mapping | Foundation | Discovery | Define demand, eligibility and supply signals | Prototype routing rules | Recommendation | Q3 build decision
Bet 1: OP → OD | Delivered orders ÷ placed orders | Discard rate, cancellation rate, first-call pickup, successful connection, call-to-confirmation, false-substitution cancellation | HA substitution context — multiple options and No-Subs-Taken history | Experiment | Discovery + Build | Validate option/ranking logic and success metric | Controlled rollout | Measure acceptance and cancellation | Scale / iterate / stop
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | Customer-contact and CPO baseline | Foundation | Build | Define order/contact/case model and cost cuts | Launch baseline reporting | Identify top cost and productivity leaks | CPO driver baseline available
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | Kapture-to-order mapping and case taxonomy | Foundation | Build | Define mapping and reason taxonomy | Build / pilot mapping for priority cases | Expand and measure quality | Order-related vs non-order contact baseline
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | CSR actioning in Kapture — refund tickets, relevant order context and priority actions | Impact | Discovery + Build | Scope priority actions and access needs | Build first workflow | Measure FCR / AHT / escalations | Priority CSR workflow live
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | L2/L3 accountability flow — email to Kapture, then Confluence/Jira | Impact | Build | Define ownership and ticket lifecycle | Implement priority flows | Adoption review | Trackable escalation ownership
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | Remove CSR dependency on Pharmacist Portal | Foundation | Discovery | Identify CSR-required actions and data | Define role-specific workspace scope | Prioritisation decision | Q3 migration plan
Bet 2: CPO & Productivity | Operating CPO / delivered order | Doctor confirmations per active hour, HA confirmations per paid hour, CSR FCR, AHT, contacts per order, repeat contacts | Chatbot foundation | Foundation | Conditional Discovery | — | Context / decision-tree readiness check | Scope only if prerequisites are ready | Q3 recommendation
Bet 3: Online Payments | Successfully prepaid orders ÷ payment-eligible orders | Payment selection, initiation, completion, finality, payment-related cancellation, payment-support contacts | Juspay Integration | Impact | Build | Integration start and event contract | Controlled traffic / validation | Scale-readiness decision | Controlled rollout path confirmed
Bet 3: Online Payments | Successfully prepaid orders ÷ payment-eligible orders | Payment selection, initiation, completion, finality, payment-related cancellation, payment-support contacts | Payment funnel instrumentation | Foundation | Build | Define eligibility → exposure → selection → payment → order outcome funnel | Launch dashboards / cohort cuts | Identify highest-leak stages | Decision-ready funnel baseline
Bet 3: Online Payments | Successfully prepaid orders ÷ payment-eligible orders | Payment selection, initiation, completion, finality, payment-related cancellation, payment-support contacts | Payment flow changes for higher online-payment contribution | Experiment | Discovery + Pilot | Customer research and experiment backlog | Run selected CTA / flow / reassurance tests | Read results and decide | Winning experiment scale plan
Bet 3: Online Payments | Successfully prepaid orders ÷ payment-eligible orders | Payment selection, initiation, completion, finality, payment-related cancellation, payment-support contacts | Payment correctness monitoring — pending, mismatch, duplicate payment, refund, paid-vs-payable | Correctness | Monitor + Fix | Baseline issue map | Fix priority gaps | Validate stability | No material known correctness regression
Bet 3: Online Payments | Successfully prepaid orders ÷ payment-eligible orders | Payment selection, initiation, completion, finality, payment-related cancellation, payment-support contacts | Partial COD / selective COD policy | Experiment | Discovery only | Define permissible cohorts and guardrails | Evidence review | Decision on controlled test | Test / defer to Q3
Bet 4: Trust & Retention | Repeat purchase / retention for eligible cohorts | Refund TAT, app self-service adoption, repeat contacts, TM Wallet correctness, substitute retention | Returns & Refunds — Milestone 1: app-first initiation and Return Tracker scale-up | Impact | Build / Scale | Finalise eligible journey and scale plan | Increase app coverage | Measure inbound-call shift | App-first returns materially expanded
Bet 4: Trust & Retention | Repeat purchase / retention for eligible cohorts | Refund TAT, app self-service adoption, repeat contacts, TM Wallet correctness, substitute retention | Returns & Refunds — Milestone 2: evidence, status, eligibility and decisioning | Impact | Discovery + Build | Scope decision flow and customer communication | Build selected workflow | Measure outbound/manual reduction | Next automation-ready flow defined
Bet 4: Trust & Retention | Repeat purchase / retention for eligible cohorts | Refund TAT, app self-service adoption, repeat contacts, TM Wallet correctness, substitute retention | Returns & Refunds — Milestone 3: low-risk refund automation | Experiment | Discovery | Identify low-risk cases and guardrails | Validate rules / operations readiness | Decision | Pilot in Q3 or limited Q2 test
Bet 4: Trust & Retention | Repeat purchase / retention for eligible cohorts | Refund TAT, app self-service adoption, repeat contacts, TM Wallet correctness, substitute retention | TM Wallet correctness | Correctness | Fix | Error taxonomy and priority issues | Fix ledger / expiry / visibility gaps | Validate customer and CSR impact | Correctness and support-impact improvement
Bet 4: Trust & Retention | Repeat purchase / retention for eligible cohorts | Refund TAT, app self-service adoption, repeat contacts, TM Wallet correctness, substitute retention | Substitute retention baseline | Foundation | Build | Define accepted-substitute linkage and retention window | Launch baseline cuts | Review behaviour | Evidence for future substitute strategy
Committed Carryover: Ring AI Pilot | Human-agent conversion from Ring-qualified leads to placed orders | Agent conversion, overall abandoned-cart recovery, human calls/minutes per recovered order, qualification quality, lead ageing | Ring AI Pilot | Pilot | Non-negotiable | Pilot setup, ownership, event tracking | Controlled live pilot | Scale / iterate / stop decision | Evidence-backed Phase 2 decision