## Read Me
Truemeds - Q2 Roadmap (July-September) - v1 Draft
Quarter | Q2 = July, August, September (fiscal year starts April)
Owner | Apurva - Portals (Doctor, HA, Assisted Commerce, CSR) and Payments
Capacity used for this cut | 1 SPM, 0 APM, 4 SDE2 + 2 SDE1 (6 engineers)
Baseline status | This quarter's roadmap is intentionally raw - most initiatives show 'baseline to be established' rather than actual figures. From next quarter, planning starts earlier with proper baseline metrics in place.
Structure | 1 hard gate (Compliance) + 4 outcome-led business bets + 1 non-negotiable carryover (Ring), tracked separately. Full bet names and their one primary metric live on the 'Bet Definitions' tab - the 'Bet' column on the roadmap sheet uses short tags only, for filtering.
Supersedes | Q2_Product_Roadmap_Draft.xlsx (earlier draft) and corrects the quarter-label inconsistency in Claude_Context_Handoff_Q3_Roadmap.md
How to use | Filter the 'Q2 Roadmap' sheet by Bet, Type, or Q2 Role. 'Bet Definitions' sheet has the one primary outcome metric per bet - it is not repeated on every roadmap row.

## Bet Definitions
Bet (tag) | Full Name | Status | Primary Outcome Metric | Notes
Compliance | Hard Gate: Compliance & Doctor Quality | Non-negotiable | 100% auditable Doctor interactions; zero confirmed impersonation | Not scored against growth/cost. Doctor identity/anti-impersonation audit work is Discovery-only this quarter (user decision).
OP -> OD | Bet 1: Order Placed -> Order Delivered | Core business bet | Delivered orders / total placed orders | Discard rate, cancellation rate, first-call pickup are guardrail/output metrics, not separate bets.
CPO | Bet 2: CPO & Productivity | Core business bet | Operating cost per delivered order (CPO) | Finance-aligned official definition still needed.
Payments | Bet 3: Online Payments | Core business bet | Successfully prepaid orders / payment-eligible orders | OP -> OD is a secondary guardrail for this bet, not its primary metric.
Retention | Bet 4: Trust & Retention | Core business bet | Repeat purchase / retention for eligible cohorts | Refund TAT, Wallet correctness, repeat contacts are drivers, not the primary metric.
Ring | Ring AI Pilot | Committed carryover - tracked separately | Human-agent conversion from Ring-qualified leads to placed orders | Pre-order / abandoned-cart recovery. Not scored against OP -> OD.

## Q2 Roadmap
Bet | Initiative | Output Metric (this initiative) | Type | Q2 Role | Jul | Aug | Sep | Sept Decision | Notes
Compliance | New Doctor Portal service - dedicated frontend, decoupled from Pharmacist Portal | New service live for Doctor traffic | Foundation | Build | Stand up service + shell | Migrate consultation workflow onto it | Cutover / stabilize | Scale / Iterate | All other Hard Gate rows below depend on this landing first
Compliance | Onboarding, auth, credentialing, prescription doc generation | Valid, signed prescription coverage | Impact | Build | Blocked on new service | Build on new service | Rollout | Scale / Iterate | Depends on row above landing in July
Compliance | Multi-patient prescription capture | % multi-patient cases correctly captured | Impact | Build | Blocked on new service | Build on new service | Rollout | Scale / Iterate | Depends on new-service row; DocStat pattern used as reference
Compliance | Case assignment & availability backbone | Assignment latency, doctor utilization | Foundation | Build (capacity-conditional) | Scope | Build | Measure | Scale / Take to Q3 | First item to slip if capacity is tight
Compliance | Doctor identity & anti-impersonation audit | Audit coverage % | Foundation | Discovery | Discovery | Discovery | Recommendation | Take to Q3 | Interim mitigation: bind session to one credentialed doctor as part of new-service auth build
OP -> OD | Doctor/HA contact & connectivity baseline (attempt capture, first-call pickup, first connection rate) | First-call pickup rate, attempt-count accuracy | Foundation | Build | Define event model | Launch tracking | Review cohorts | Scale / Iterate | Committed/Required
OP -> OD | Connectivity fix - missed-call recovery + number-health/spam control | First-call pickup, callback-to-confirmation | Impact | Build | Scope callback flow + number-health baseline | Launch HA-first callback + selected controls | Measure pickup impact | Scale / Iterate | Merged from 2 items for SPM bandwidth
OP -> OD | Contact routing discovery - demand-supply mapping + customer-first pre-connect pilot | Routing recommendation, pilot cohort read | Foundation / Experiment | Discovery | Define demand/supply signals | Small pre-connect pilot if capacity allows | Recommendation | Take to Q3 | Merged from 2 items; pre-connect pilot conditional
OP -> OD | HA substitution context - multiple options, No-Subs-Taken history, false-substitution cancellation tracking | Substitution acceptance, false-substitution cancellation rate | Experiment | Discovery + Build | Validate option/ranking logic | Controlled rollout | Measure acceptance & cancellation | Scale / Iterate / Stop | Includes committed tracking item
CPO | Kapture foundation - customer-contact/CPO baseline + order mapping + case taxonomy | Order-mapped contact % | Foundation | Build | Define model & mapping | Launch baseline + mapping | Identify cost/productivity leaks | Scale / Iterate | Committed/Required; merged from 3 items
CPO | CSR workflow build - priority actioning in Kapture + L2/L3 accountability flow | CSR FCR, AHT, escalation ownership | Impact | Build | Scope priority actions | Build workflow (sequenced after Kapture foundation) | Measure FCR/AHT/adoption | Scale / Iterate | Depends on Kapture foundation landing first
CPO | Remove CSR dependency on Pharmacist Portal | CSR-required actions migrated off shared portal | Foundation | Discovery | Identify CSR-required actions | - | Prioritisation decision | Take to Q3 | Chatbot foundation cut from Q2 entirely - prerequisite work not ready
Payments | Juspay integration | Payment completion, finality | Impact | Build | Integration start + event contract | Controlled traffic / validation | Scale-readiness decision | Scale / Iterate | Committed
Payments | Payment funnel instrumentation | Funnel stage conversion | Foundation | Build | Define funnel + eligibility cuts | Launch dashboards | Identify highest-leak stage | Scale / Iterate | Committed/Required
Payments | Payment-flow experiments for higher online contribution | Prepaid selection rate | Experiment | Discovery + Pilot | Research + experiment backlog | Run selected tests | Read results | Scale winning test
Payments | Payment correctness monitoring - pending/mismatch/duplicate/refund/paid-vs-payable | Correctness exception rate | Correctness | Monitor + Fix | Baseline issue map | Fix priority gaps | Validate stability | Iterate
Payments | Partial COD / selective COD policy | Eligible-cohort definition | Experiment | Discovery only | Define permissible cohorts | Evidence review | Decision on controlled test | Take to Q3 | Narrow, evidence-led only - no rollout commitment
Retention | Returns & Refunds - M1: app-first initiation + Return Tracker scale-up | App-first initiation %, inbound-call shift | Impact | Build / Scale | Finalize journey + scale plan | Increase app coverage | Measure inbound shift | Scale / Iterate
Retention | Returns & Refunds - M2: evidence, status, eligibility, decisioning | Outbound/manual reduction | Impact | Discovery + Build (conditional on M1) | Scope decision flow | Build only if M1 coverage on track | Measure reduction | Scale / Iterate / Take to Q3 | Explicitly conditional on M1 progress, not parallel-track
Retention | Returns & Refunds - M3: low-risk refund automation | Automated decision accuracy | Experiment | Discovery | Identify low-risk cases | Validate rules/ops readiness | Decision | Take to Q3
Retention | TM Wallet correctness | Wallet error rate, support-ticket reduction | Correctness | Fix | Error taxonomy + priority issues | Fix ledger/expiry/visibility gaps | Validate impact | Iterate
Retention | Substitute retention baseline | Accepted-substitute repeat-purchase linkage | Foundation | Build | Define linkage + window | Launch baseline cuts | Review behaviour | Scale / Iterate
Ring | Ring AI Pilot | Agent conversion %, calls/min per recovered order | Pilot | Non-negotiable | Pilot setup, ownership, event tracking | Controlled live pilot | Scale/iterate/stop decision | Scale / Iterate / Stop | Committed carryover; tracked separately from the 4 bets